## Sheet1
Tasks and Assignment Breakdown
| Group: | Group 7
| Team Members (and initials): | Kaegan Koski, Robert Mimms, Hiro Nakae, Peyton Phillips
| Date this was last updated: | 2026-05-04 12:38
| Last updated by (whom): | RM
In general, you should archive a copy of this spreadsheet (with the date in the file name) before modifying it.
(The tasks can be grouped by week, major activity or other. You can delete this row from the spreadsheet.)
Grouping | Task or Milestone (with an objectively verifiable completion) | Status | Assigned to (whom) | Date Assigned | Anticipated Time (hours) | Date Due | Date Completed | Completed by (whom) | Time Spent (hours) | Confirmed Completed by (whom) | Date Confirmed Complete | Notes
Requirements
| Have initial meeting with client to review v1 of SRS. |  | All | 2026-04-11 | 0.5 | 2026-04-14 |  | All | 0.5 | All | 2026-04-11
| Write up summary of client meeting. Post on shared repository |  | All |  | 0.5
| Create test-assignment breakdown instead of Gannt chart |  | PP | 2026-04-11 | 1 | ASAP | 2026-04-11 | PP | 2 | All | 2026-05-04 | Updated periodically, only listed creation date here.
| Have secondary meeting with client to confirm project progress and have check in |  | All | 2026-04-28 | 0.5 | 2026-04-29 |  | All | 0.5 | All | 2026-04-28
| Presentation |  | All | 2026-05-05 | 0.1
Design
| Generate v1 of SDS. Post on shared google drive. |  | KK, PP | 2026-04-14 | 3 | 2026-04-15 | 2026-04-14 | KK, PP | 4 | All | 2026-04-15
| Generate v1 of SRS. Post on shared google drive |  | PP | 2026-04-14 | 3 | 2026-04-15 | 2026-04-14 | PP | 4 | All | 2026-04-15
| Generate v1 of project plan documentation. Post on shared google drive |  | PP | 2026-04-14 | 3 | 2026-04-15 | 2026-04-14 | PP | 4 | All | 2026-04-15 | SRS, SDS, Project plan all under 1 document called initial submission
| Generate v2 of SDS. Post on shared google drive |  | KK, PP | 2026-04-29 | 5 | 2026-05-04 |  | KK, PP |  | All | 2026-05-04
| Generate v2 of project plan. Post shared on google drive |  | PP | 2026-04-29 | 5 | 2026-05-04 |  | PP |  | All | 2026-05-04 | Deleted SRS from document and made changes to SDS and Project Plan described in email
| Generate slidedeck for presentation |  | All | 2026-05-01 | 2 | 2026-05-05 |  | All |  |  |  | Slidedeck for presentation. Each person worked on their own slide part
Git Commits
| First commit |  | HN | 2026-04-10 |  | 2026-04-16 | 2026-04-11 | HN |  |  |  | Create repository
| Npx create-next-app@latest |  | HN | 2026-04-10 |  | 2026-04-16 | 2026-04-11 | HN |  |  |  | Create next.js application with pre-configured environment
| readme.md format |  | HN | 2026-04-10 |  | 2026-04-16 | 2026-04-11 | HN |  |  |  | Edited readme.md
| Getting started (1) |  | HN | 2026-04-10 |  | 2026-04-16 | 2026-04-12 | HN
| Getting started (2) |  | HN | 2026-04-10 |  | 2026-04-16 | 2026-04-12 | HN
| Add Roberts project proposal to readme |  | HN | 2026-04-10 |  | 2026-04-16 | 2026-04-12 | HN
| Test |  | PP | 2026-04-13 |  | 2026-04-16 | 2026-04-13 | PP |  |  |  | Git commit check to make sure everyone received the same access to the repository
| Add SDS doc to readme |  | HN | 2026-04-13 |  | 2026-04-16 | 2026-04-13 | HN
| skeleton(api): add python FastAPI directory |  | HN | 2026-04-13 |  | 2026-04-16 | 2026-04-14 | HN
| feat(GradeChart): initial setup for chart.js |  | HN | 2026-04-13 |  | 2026-04-16 | 2026-04-14 | HN
| Setup: sqlite3 |  | HN | 2026-04-13 |  | 2026-04-16 | 2026-04-14 | HN
| Setup: docker-compose |  | HN | 2026-04-13 |  | 2026-04-16 | 2026-04-14 | HN
| Readme: roles/fastapi |  | HN | 2026-04-13 |  | 2026-04-16 | 2026-04-14 | HN
| Setup: configuration files |  | HN | 2026-04-13 |  | 2026-04-16 | 2026-04-14 | HN
| setup(app): stats route skeleton |  | HN | 2026-04-13 |  | 2026-04-16 | 2026-04-14 | HN
| setup: vitest config |  | HN | 2026-04-13 |  | 2026-04-16 | 2026-04-14 | HN
| Readme: git push rules (version control protocol) |  | HN | 2026-04-13 |  | 2026-04-16 | 2026-04-14 | HN
| Mockup (design+implementation): skeleton |  | HN | 2026-04-13 |  | 2026-04-16 | 2026-04-14 | HN
| milestone1(ui): initial design |  | HN | 2026-04-10 |  | 2026-04-16 | 2026-04-16 | HN
| database.py creation |  | RM | 2026-04-13 |  |  | 2026-04-18 | RM | 4 |  |  | Implemented the python code to create the SQLite database, sanitize the data, and populate the database with that CSV data.
| Moved database.py to ~/db/ |  | HN | 2026-04-18 |  |  | 2026-04-18 | HN
| Update requirements.txt |  | HN | 2026-04-18 |  |  | 2026-04-18 | HN
| setup(makefile): scripts |  | HN | 2026-04-18 |  |  | 2026-04-24 | HN
| Debug |  | HN | 2026-04-18 |  |  | 2026-04-25 | HN |  |  |  | Fix data flow - display top professors by gpa - api endpoints - fix db pathing - admin page manages degree requirements
| Course data cleaning |  | KK | 2026-04-18 |  |  | 2026-04-26 | KK |  |  |  | Very cumbersome cleaning of course data so it only shows courses that are noted for the degree plan.
| CSmajor stuff |  | HN | 2026-04-26 |  |  | 2026-04-26 | HN
| Degree planner, improved UI |  | HN | 2026-04-26 |  |  | 2026-04-26 | HN
| Expected GPA shown for plan |  | KK | 2026-04-26 |  |  | 2026-04-26 | KK
| Minor change |  | KK | 2026-04-26 |  |  | 2026-04-26 | KK |  |  |  | Minor removal of log and addition of updating expected grade on removal of course
| TestAPI |  | KK | 2026-04-26 |  |  | 2026-04-26 | KK |  |  |  | Added TestAPI class to test_main.py file. Added some quick tests for database interaction from the api
| Fix tests directory: removed parenthesis |  | HN | 2026-04-28 |  |  | 2026-04-28 | HN
| Pytest for api/db, vitest for app |  | HN | 2026-04-28 |  |  | 2026-04-28 | HN
| Comments and refactoring of tests |  | KK | 2026-05-01 |  |  | 2026-05-01 | KK
| UI: sorted and toggled years on load |  | HN | 2026-04-28 |  |  | 2026-05-01 | HN
| Add math major requirements |  | HN | 2026-04-28 |  |  | 2026-05-01 | HN
| Test_main.py changed to use copy of database. Adds way to specify database in api/main.py |  | KK | 2026-05-01 |  |  | 2026-05-01 | KK
| Makefile changes |  | KK | [8 empty] | Removed personal changes to makefile
| Admin page: major reqs for cs math and business |  | HN | 2026-04-28 |  |  | 2026-05-01 | HN
| Audit(fix): removed dead code and unused packages |  | HN | 2026-04-28 |  |  | 2026-05-01 | HN
| Add useState hook for planItems + bug fix: major selector and selected degree plan interaction |  | HN | 2026-04-28 |  |  | 2026-05-01 | HN
| UI: search by teacher put in sidebar |  | HN | 2026-04-28 |  |  | 2026-05-01 | HN
| UI: saved plans and buttons |  | HN | 2026-04-28 |  |  | 2026-05-01 | HN
| Doc (how to fix node version to 22): see maintenance.md |  | HN | 2026-04-28 |  |  | 2026-05-02 | HN
| feat(gen-plan): won’t override manually selected courses |  | HN | 2026-04-28 |  |  | 2026-05-02 | HN
| UX/UI(generating/editing): your plan |  | HN | 2026-04-28 |  |  | 2026-05-02 | HN
| UI(filter-sidebar): improve ux |  | HN | 2026-04-28 |  |  | 2026-05-02 | HN
| UI/UX(course-card): feature + tests + documentation |  | HN | 2026-04-28 |  |  | 2026-05-02 | HN
| Vercel bug fix(attempt): remove shut from requirements.txt |  | HN | 2026-04-28 |  |  | 2026-05-02 | HN
| UI/UX(student My Degree Plan page): default collapsed, sorted |  | HN | 2026-04-28 |  |  | 2026-05-02 | HN
| Dashboard(UI/Feat): sorting + grid layout |  | HN | 2026-04-28 |  |  | 2026-05-02 | HN
| Added functionality to the csv uploader |  | KK | 2026-04-28 |  |  | 2026-05-02 | KK |  |  |  | Added functionality to the CSV uploader so the csv is saved to the DB directory. NO FUNCTIONALITY PLUGGING THAT INTO DB YET
| Added tests to test_main.py |  | PP | 2026-05-01 |  |  | 2026-05-02 | PP |  |  |  | Added tests to test_main.py in api tests. Currently passes all added tests.
| UI(instructors) + UI/UX(add visual emphasis to course when navigate from requirements section) |  | HN | 2026-04-28 |  |  | 2026-05-02 | HN
| Performance(app): cache more, lazy load, useMemo, useTransition, remove dead code/assets/directories |  | HN | 2026-04-28 |  |  | 2026-05-03 | HN
| Revert previous commit (Performance(App)) |  | HN |  |  |  | 2026-05-03 | HN
| database.py edits |  | RM | 2026-04-28 |  |  | 2026-05-03 | RM | 3 |  |  | Edited database.py to accept new CSV files and check ~/data/raw for grade data and ~/data/meta for major requirements. API can either call the _load functions for grade history and major requirements, or drop them in the appropriate folders and run make db-init. Added db_init and db_test targets for the makefile. db_test runs through various functions of the database as well as edge cases and outliers
| Implemented CSV uploading from front end to backend |  | KK | 2026-04-28 |  |  | 2026-05-03 | KK
| Add course titles to DB |  | HN | 2026-04-28 |  |  | 2026-05-03 | HN
| Fix(tests): rename CourseTitles to Course_Titles and add course title pipeline |  | HN | 2026-04-28 |  |  | 2026-05-03 | HN
| Save course titles (import grade data) |  | HN | 2026-04-28 |  |  | 2026-05-03 | HN
| Added test for CSV uploading api function |  | KK | 2026-05-01 |  |  | 2026-05-03 | KK
| Minor change to database.py |  | KK | 2026-05-01 |  |  | 2026-05-03 | KK
| Verify(functional requirements): implemented year-range filter |  | HN | 2026-04-28 |  |  | 2026-05-03 | HN
| Feat: add CSV import preview/confirm flow and fix |  | HN | 2026-04-28 |  |  | 2026-05-03 | HN
| Feat: add degree-plan CSV import and extract RequirementsChecklist component |  | HN | 2026-04-28 |  |  | 2026-05-03 | HN
| Milestone(Finish last functional requirement) |  | HN | 2026-04-28 |  |  | 2026-05-03 | HN |  |  |  | Implemented FR 2.2.3 reconciliation file support
| submission_artifacts/ |  | HN | 2026-04-28 |  |  | 2026-05-04 | HN |  |  |  | Folder for submission
| Placeholders for submission artifacts folder |  | HN | 2026-04-28 |  |  | 2026-05-04 | HN |  |  |  | Placeholder files